Buydens Sam

r0884392

October 5, 2025

Removing system linearity requirements through reference cancelation in Data Converters

Thesis Planning

Introduction

I divided my ECTS credits roughly equally between the two semesters of my second master year, this is why I will be aiming to put roughly the same amount of time into my this during the first semester and second semester.

Time division and goals

20 % Literature Study

- Reading papers about ADCs to learn how the latest technology deals with non-linearity.

50 % System level simulation

- Creating a high level system and simulating it in matlab.

30 % circuit level simulation

- Realizing the system on circuit level and simulating it.

Estimation of amount of time planned in each month (total time should be 600-720 hours).

| Month | Hours | Days | Hours per day |
| --- | --- | --- | --- |
| October | 63 | 21 | 4 |
| November | 69 | 23 | 4 |
| December | 21 | 7 | 4 |
| January | 0 | 0 | 4 |
| February | 112 | 28 | 4 |
| March | 124 | 31 | 4 |
| April | 120 | 30 | 4 |
| May | 45 | 15 | 4 |
| Total | 620 | 155 |  |

Notes:

- Some weeks will be occupied by projects of other courses which I have included in the estimation.

- The period before the exams and during the exams have also been left out of the estimation since I plan to focus on exams than although I might still work on my thesis if I have some time.

Proceedings:

| Date | activity |
| --- | --- |
| 20 October | Finish literature review |
| 27 November | Interim presentation |
| 7 December | Finished top level system design |
| 28 February | Finished matlab simulations |
| 15 May | Finished writing thesis text |
| 4 June | Submission deadline |

Conclusion

This document is an initial estimate of how the thesis will proceed throughout the year. With this I have clearly stated which goals I have to achieve by when which will help me keep progress.